## Sayfa1
TASK | RESPONSIBILITY | START | END | Sept | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June
|  |  |  | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Week number |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Project Management Plan (PMP) | Program Engineer | 13 10 2025 | 20 11 2025 | bar: October 42 4 to November 47 9
Requirements capture | System Engineer | 2025-10-25 | 2025-10-30 | bar: October 42 4 to October 43 5; November 46 8
Conceptual Design | Everyone | 13 10 2025 | 2025-11-07 | bar: October 42 4 to November 46 8
Design Description | System Engineer | 2025-10-25 | 2025-11-07 | bar: October 44 6 to November 46 8
Configuration Item List | System Engineer | 2025-10-25 | 2025-11-07 | bar: October 44 6 to November 46 8
Preliminary Design Review (PDR) | Program Engineer | 2025-11-01 | 2025-11-23 | bar: November 46 8
Detailed Design |  | 2025-11-23 | 2026-01-07 | bar: November 46 8; November 48 10 to January 1 15
Electronic Design (CAD/CAM, Assembly Drawings) | Electronics Engineer | 2025-11-23 | 2026-12-27 | bar: November 46 8; November 48 10 to December 51 13
Mechanical Design (CAD/CAM) | Mechanical Enginer | 2025-11-23 | 2026-12-27 | bar: November 48 10 to December 51 13
Software design, test, document | Software Engineer | 2025-11-23 | 2026-12-27 | bar: November 48 10 to December 51 13
Purchasing | Electronics Engineer | 2025-11-23 | 2026-12-27 | bar: November 48 10 to December 51 13
Critical Design Review | Program Engineer | 2025-12-27 | 2026-01-07 | bar: December 52 14
Implementation (Prototype Production, V2T) |  | 2026-01-05 | 2026-03-29 | bar: January 1 15 to April 15 29
3D Printing | Mechanical Engineer | 2026-01-05 | 2026-03-05 | bar: January 1 15 to March 10 24
PCB Assembly, Wiring Assembly production, ICT, Fabtest, Marking) | Production Engineer | 2026-01-01 | 2026-03-05 | bar: January 1 15 to March 10 24
Workmanship Inspection, NCR | QA Engineer | 2026-01-19 | 2026-03-05 | bar: January 1 15 to March 10 24
Software test, finalizing software | Software Engineer | 2026-01-19 | 2026-03-05 | bar: January 1 15 to March 10 24
Thermometer Assembly drawing | System Engineer | 2026-02-02 | 2026-03-05 | bar: January 1 15 to March 10 24
Top assembly production | Mechanical Engineer | 2026-02-16 | 2026-03-05 | bar: January 1 15 to March 10 24
Acceptance Test Procedure (ATP) | QA Engineer | 2026-02-02 | 2026-03-14 | bar: February 6 20 to March 11 25
Test setup | System Engineer | 2026-02-02 | 2026-03-14 | bar: February 6 20 to March 11 25
Acceptance Test | Group Task | 2026-02-02 | 2026-03-14 | bar: February 6 20 to March 11 25
Verification/Validation Test Plan | QA Engineer | 2026-02-16 | 2026-03-01 | bar: February 8 22 to February 9 23
Verification/Validation Test Procedure | Software Engineer | 2026-03-01 | 2026-03-14 | bar: March 10 24 to March 11 25
Verification/Validation Tests | Group Task | 2026-03-14 | 2026-03-28 | bar: March 12 26 to March 13 27
Implementation Review | Alper Demirhan | 2026-04-01 | 2026-04-10 | bar: April 14 28
Supporting Processes |  | 2025-11-03 | 2026-05-25 | bar: October 44 6 to May 22 36
Quality Assurance (Audit, CA, NCR, V2T plan, ATP) | QA Engineer | 2025-10-29 | 2026-03-14 | bar: October 44 6 to March 11 25
Configuration Management | System Engineer | 2025-10-29 | 2026-04-10 | bar: October 44 6 to April 15 29
Risk Management | Program Engineer | 2025-11-17 | 2025-11-23 | bar: November 46 8 to November 47 9
Procurement (purchasing) | Electronics Engineer | 2025-11-24 | 2026-03-14 | bar: November 46 8; November 48 10 to December 51 13; March 10 24 to March 11 25
Monthly Reports | Program Engineer | 2025-11-24 | 2026-05-25 | bar: November 46 8; November 48 10; December 52 14; January 5 19; February 9 23; March 13 27; April 18 32; May 22 36